## 533M with data
2. REPORT FOR MONTH ENDING AND NUMBER
| NATIONAL AERONAUTICS AND SPACE ADMINISTRATION | [6 empty] | Form Approved |  | OF WORKING DAYS
| MONTHLY CONTRACTOR FINANCIAL MANAGEMENT REPORT | [6 empty] | O.M.B. No. 2700-0003 |  | 1991-05-31
TO: | Jet Propulsion Laboratory |  |  |  | FROM: | Acme Aerospace Co |  |  |  | 3. CONTRACT VALUE
| 4800 Oak Grove Drive |  |  |  |  | 2020 Electronics Way |  |  |  | a. COST |  | b. FEE
| Pasadena, CA 91109 c/o I. Buythings, Contract Negotiator |  |  |  |  | South Bay, CA 90200 |  |  |  | 10500 |  | 840
| a. TYPE |  |  |  | b. CONTRACT NO. AND LATEST DEFINITIZED MODIFICATION NO. |  |  |  |  | 4. FUND LIMITATION
1. DESCRIPTION |  | Cost Plus Fixed Fee |  |  |  | 959000 Mod 5 |  |  |  | 6300 | (Mod 5)
OF
CONTRACT | c. SCOPE OF WORK |  |  |  | d. AUTHORIZED CONTRACTOR REPRESENTATIVE (Signature) |  |  |  | DATE | 5. BILLING
[10 empty] | a. INVOICE AMTS. BILLED |  | b. TOTAL PYTS.
|  | Spacecraft Subsystem | [6 empty] | 1991-06-13 | 4953 |  | REC'D: $4,289
[10 empty] | Inv. No. 82335 |  | (5/20/91)
|  |  | 7. COST INCURRED/HOURS WORKED |  |  |  | 8. ESTIMATED COST/HOURS TO COMPLETE |  |  | 9. ESTIMATED FINAL
|  |  | DURING MONTH |  | CUM. TO DATE |  | DETAIL |  |  | COST/HOURS |  | 10. UNFILLED
| 6. REPORTING CATEGORY | [7 empty] | BALANCE OF | CONTRACTOR | CONTRACT | ORDERS
|  |  | ACTUAL | PLANNED | ACTUAL | PLANNED | 1991-06-01 | 1991-07-01 | CONTRACT | ESTIMATE | VALUE | OUTSTANDING
|  |  | a. | b. | c. | d. | a. | b. | c. | a. | b.
ENGINEERING DIRECT LABOR HOURS |  |  | 7.7 | 6.8 | 61.6 | 64 | 7.5 | 7.2 | 49.1 | 125.4 | 125.4
MANUFACTURING DIRECT LABOR HOURS |  |  | 0.3 | 0.8 | 1.9 | 5 | 0.8 | 1.2 | 16.1 | 20 | 20
TOTAL DIRECT LABOR HOURS |  |  | 8 | 7.6 | 63.5 | 69 | 8.3 | 8.4 | 65.2 | 145.4 | 145.4
ENGINEERING DIRECT LABOR DOLLARS |  |  | 175 | 149 | 1417 | 1402 | 173 | 166 | 1129 | 2885 | 2748
MANUFACTURING DIRECT LABOR DOLLARS |  |  | 4 | 11 | 25 | 69 | 11 | 16 | 212 | 264 | 276
TOTAL DIRECT LABOR DOLLARS |  |  | 179 | 160 | 1442 | 1471 | 184 | 182 | 1341 | 3149 | 3024
ENGINEERING OVERHEAD |  |  | 209 | 178 | 1715 | 1675 | 209 | 201 | 1366 | 3491 | 3300
MANUFACTURING OVERHEAD |  |  | 14 | 39 | 89 | 244 | 39 | 57 | 755 | 940 | 976
TOTAL OVERHEAD |  |  | 223 | 217 | 1804 | 1919 | 248 | 258 | 2121 | 4431 | 4276
MATERIALS |  |  | 60 | 20 | 759 | 549 | 123 | 90 | 251 | 1223 | 843 | 322
SUBCONTRACTS |  |  | 28 | 30 | 400 | 420 | 100 | 100 |  | 600 | 600 | 100
OTHER DIRECT COSTS |  |  | 17 | 12 | 225 | 182 | 20 | 20 | 213 | 478 | 387
TOTAL PRODUCTION COSTS |  |  | 507 | 439 | 4630 | 4541 | 675 | 650 | 3926 | 9881 | 9130
G&A |  |  | 76 | 66 | 694 | 681 | 101 | 97 | 588 | 1480 | 1370
TOTAL COST |  |  | 583 | 505 | 5324 | 5222 | 776 | 747 | 4514 | 11361 | 10500
FEE |  |  | 47 | 40 | 426 | 418 | 53 | 51 | 310 | 840 | 840
TOTAL COST PLUS FEE |  |  | 630 | 545 | 5750 | 5640 | 829 | 798 | 4824 | 12201 | 11340
Baseline Plan Identification (Col 7b & 7d): Revision No. ___1__________________________________ , Dated ____2/15/91_____________
NASA FORM 533M AUG96 PREVIOUS EDITIONS ARE OBSOLETE. |  |  |  |  | Dollars in Thousands
Hours in Thousands

## 533Q with data
2. REPORT FOR QUARTER BEGINNING
NATIONAL AERONAUTICS AND SPACE ADMINISTRATION | [7 empty] | Form Approved
QUARTERLY CONTRACTOR FINANCIAL MANAGEMENT REPORT | [7 empty] | O.M.B. No. 2700-0003 | [7 empty] | 1991-07-01
TO: | Jet Propulsion Laboratory |  |  |  | FROM: | Acme Aerospace Co | [9 empty] | 3. CONTRACT VALUE
| 4800 Oak Grove Drive |  |  |  |  | 2020 Electronics Way | [9 empty] | a. COST |  | b. FEE
| Pasadena, CA 91109 c/o I. Buythings, Contract Negotiator |  |  |  |  | South Bay, CA 90200 | [9 empty] | 10500 |  | 840
| a. TYPE |  |  |  | b. CONTRACT NO. AND LATEST DEFINITIZED MODIFICATION NO. | [10 empty] | 4. FUND LIMITATION
1. DESCRIPTION |  | Cost Plus Fixed Fee |  |  |  | 959000 Mod 5 | [9 empty] | 6300
OF | [15 empty] | (Mod 5)
CONTRACT | c. SCOPE OF WORK |  |  |  | d. AUTHORIZED CONTRACTOR REPRESENTATIVE (Signature) | [9 empty] | DATE | 5. BILLING
[16 empty] | a. INVOICE AMTS. BILLED |  | b. TOTAL PYTS. REC'D
|  | Spacecraft Subsystem | [12 empty] | 1991-06-13 | 4953 |  | 4289
[16 empty] | Inv. No. 82335 |  | (5/20/91)
|  |  | 7. COST INCURRED/HOURS WORKED |  |  |  | 8. ESTIMATED COST/HOURS TO COMPLETE | [8 empty] | 9. ESTIMATED FINAL |  |  | 11. UN-
|  |  | CUM ACT |  |  | MONTH | MONTH | MONTH | QUARTER | QUARTER | QUARTER | BALANCE | NEXT |  |  | COST/HOURS |  | 10. EST | FILLED
| 6. REPORTING CATEGORY |  | THROUGH | CURRENT | CUM | [6 empty] | OF FY | FY | BAL | TOTAL TO | CONTRACTOR | CONTRACT | COMPL | ORDERS
|  |  | PRIOR | MONTH | EST | JUL | AUG | SEP | O-N-D | J-F-M | A-M-J | J-A-S |  | OF | COMPLETE | ESTIMATE | VALUE | DATE | OUT-
|  |  | MONTH | EST | TO DATE | 1991 | 1991 | 1991 | 1991 | 1992 | 1992 | 1992 | 1993 | CONTR |  |  |  |  | STANDING
|  |  | a. | b. | c. | a. | b. | c. | d. | e. | f. | g. | h. | i. | j. | a. | b.
ENGINEERING DIRECT LABOR HOURS |  |  | 61.6 | 7.5 | 69.1 | 7.2 | 8 | 7.8 | 21 | 12.3 |  |  |  |  | 56.3 | 125.4 | 125.4
MANUFACTURING DIRECT LABOR HOURS |  |  | 1.9 | 0.8 | 2.7 | 1.2 | 3.2 | 3.8 | 9.1 | [5 empty] | 17.3 | 20 | 20
TOTAL DIRECT LABOR HOURS |  |  | 63.5 | 8.3 | 71.8 | 8.4 | 11.2 | 11.6 | 30.1 | 12.3 |  |  |  |  | 73.6 | 145.4 | 145.4
ENGINEERING DIRECT LABOR DOLLARS |  |  | 1417 | 173 | 1590 | 166 | 184 | 179 | 483 | 283 |  |  |  |  | 1295 | 2885 | 2748
MANUFACTURING DIRECT LABOR DOLLARS |  |  | 25 | 11 | 36 | 16 | 42 | 50 | 120 | [5 empty] | 228 | 264 | 276
TOTAL DIRECT LABOR DOLLARS |  |  | 1442 | 184 | 1626 | 182 | 226 | 229 | 603 | 283 |  |  |  |  | 1523 | 3149 | 3024
ENGINEERING OVERHEAD |  |  | 1715 | 209 | 1924 | 201 | 223 | 217 | 584 | 342 |  |  |  |  | 1567 | 3491 | 3300
MANUFACTURING OVERHEAD |  |  | 89 | 39 | 128 | 57 | 150 | 178 | 427 | [5 empty] | 812 | 940 | 976
TOTAL OVERHEAD |  |  | 1804 | 248 | 2052 | 258 | 373 | 395 | 1011 | 342 |  |  |  |  | 2379 | 4431 | 4276
MATERIALS |  |  | 759 | 123 | 882 | 90 | 131 | 120 | [6 empty] | 341 | 1223 | 843 |  | 322
SUBCONTRACTS |  |  | 400 | 100 | 500 | 100 | [8 empty] | 100 | 600 | 600 |  | 100
OTHER DIRECT COSTS |  |  | 225 | 20 | 245 | 20 | 30 | 30 | 90 | 63 |  |  |  |  | 233 | 478 | 387
TOTAL PRODUCTION COSTS |  |  | 4630 | 675 | 5305 | 650 | 760 | 774 | 1704 | 688 |  |  |  |  | 4576 | 9881 | 9130
G&A |  |  | 694 | 101 | 795 | 97 | 114 | 116 | 255 | 103 |  |  |  |  | 685 | 1480 | 1370
TOTAL COST |  |  | 5324 | 776 | 6100 | 747 | 874 | 890 | 1959 | 791 |  |  |  |  | 5261 | 11361 | 10500 | 2/28/92
FEE |  |  | 426 | 53 | 479 | 51 | 60 | 61 | 135 | 54 |  |  |  |  | 361 | 840 | 840
TOTAL COST PLUS FEE |  |  | 5750 | 829 | 6579 | 798 | 934 | 951 | 2094 | 845 |  |  |  |  | 5622 | 12201 | 11340
Baseline Plan Identification (Col 7b & 7d): Revision No. ___1__________________________________ , Dated ____2/15/91_____________
NASA FORM 533Q AUG96 PREVIOUS EDITIONS ARE OBSOLETE. | [6 empty] | Dollars in Thousands
Hours in Thousands